SPENDLY

Personal Finance Tracker

PROJECT CHARTER

| Document Version | v1.0 |
| --- | --- |
| Date | March 2026 |
| Author | Nandun De Silva |
| Status | Approved |
| Repository | github.com/nandun-de-silva/spendly-app |

1.  PROJECT OVERVIEW

| Project Name | Spendly — Personal Finance Tracker |
| --- | --- |
| Project Type | Mobile Application (React Native + Expo) |
| Methodology | Agile — Scrum (4 Sprints) |
| Target Platform | Android (Google Play Store) |
| Duration | 8 Weeks (March — May 2026) |

Spendly is a cross-platform personal finance tracker mobile application built with React Native and Expo. The application enables users to record income and expenses, set monthly budgets, visualise spending patterns through interactive charts, and export transaction history. The project follows a full Agile Scrum lifecycle with complete professional BA and SE documentation at every phase.

2.  PROBLEM STATEMENT

Many individuals — particularly students and young professionals — struggle to track their personal finances effectively. Existing apps are either too complex, too expensive, or not tailored to the local context. Spendly addresses this gap by providing a simple, intuitive, offline-capable finance tracker with clear visualisations and no subscription fees.

3.  PROJECT OBJECTIVES

- Deliver a fully functional Android application deployable to Google Play Store.

- Follow Agile Scrum methodology across 4 defined sprints with regular reviews.

- Produce a complete professional documentation suite: BRS, SRS, Use Cases, ERD, DFD, Wireframes, Test Plan, and UAT.

- Demonstrate full-stack mobile development capability using React Native and TypeScript.

- Implement data visualisation, budget alerts, and CSV export features.

- Achieve 90%+ test pass rate on all defined test cases.

4.  PROJECT SCOPE

IN SCOPE:

- User authentication (local PIN or biometric)

- Income and expense transaction recording with categories and notes

- Monthly budget setting and push notification alerts

- Dashboard with charts: pie chart, bar chart, spending trend line

- Transaction history with search and filter

- CSV export functionality

- Dark and Light theme toggle

- Full BA and SE documentation suite

- Google Play Store deployment

OUT OF SCOPE:

- Bank account sync or open banking integration

- Cloud sync or multi-device support (deferred to v2.0)

- iOS App Store deployment (deferred to v2.0)

- Multi-currency support (deferred to v2.0)

- Social or sharing features

5.  PROJECT DELIVERABLES

| Deliverable | Type | Sprint |
| --- | --- | --- |
| Project Charter | Document | Sprint 1 |
| Business Requirements Spec (BRS) | Document | Sprint 1 |
| Stakeholder Register | Document | Sprint 1 |
| Risk Register | Document | Sprint 1 |
| Software Requirements Spec (SRS) | Document | Sprint 2 |
| Use Case Diagrams & Descriptions | Document | Sprint 2 |
| Entity Relationship Diagram (ERD) | Diagram | Sprint 2 |
| Data Flow Diagrams (DFD) | Diagram | Sprint 2 |
| Wireframes (Figma) | Design | Sprint 2 |
| UI Style Guide | Design | Sprint 2 |
| React Native Source Code | Code | Sprint 3 |
| Test Plan & Test Cases | Document | Sprint 4 |
| Bug Report Log | Document | Sprint 4 |
| UAT Sign-off | Document | Sprint 4 |
| Google Play Store Release | Deployment | Sprint 4 |

6.  SPRINT PLAN

| Sprint | Duration | Focus | Key Deliverables |
| --- | --- | --- | --- |
| Sprint 1 | Week 1-2 | Initiation & Planning | Project Charter, BRS, Stakeholder Register, Risk Register |
| Sprint 2 | Week 3-4 | Requirements & Design | SRS, Use Cases, ERD, DFD, Wireframes, Style Guide |
| Sprint 3 | Week 5-6 | Core Development | Auth, Transactions, Dashboard, Charts, Budget Alerts |
| Sprint 4 | Week 7-8 | Testing & Deployment | Test Plan, Test Cases, UAT, Play Store Release |

7.  STAKEHOLDERS

| Project Manager / Developer | Nandun De Silva — responsible for all development, documentation, and delivery |
| --- | --- |
| End Users | Students and young professionals managing personal finances |
| Assessors / Reviewers | Potential employers and academic reviewers evaluating the project portfolio |
| Platform Authority | Google Play Store — distribution and compliance authority |

8.  RISK REGISTER (SUMMARY)

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Scope creep adding unplanned features | Medium | High | Strict sprint backlog control; defer to v2.0 backlog |
| React Native compatibility issues | Low | Medium | Pin dependency versions; test on multiple Android versions |
| Play Store rejection | Low | High | Follow Play Store policies from day one; prepare privacy policy |
| Time overrun on documentation | Medium | Medium | Timebox each document; use templates |
| Data loss from local storage | Low | Medium | Implement AsyncStorage with backup and CSV export |

9.  ASSUMPTIONS & CONSTRAINTS

Assumptions:

- Developer has a Windows 10/11 machine with Node.js and Android Studio installed.

- Google Play Developer account ($25 one-time fee) will be registered before Sprint 4.

- Expo Go app available for physical device testing during development.

- All documentation will be version-controlled in the GitHub repository.

Constraints:

- Project is developed by a single developer within an 8-week timeframe.

- No external APIs will be integrated in v1.0.

- Budget is zero — all tools used must be free or open source.

10.  SUCCESS CRITERIA

- All 4 sprints completed within the 8-week timeline.

- Full documentation suite produced and committed to GitHub.

- Application successfully published to Google Play Store.

- All core features functional: transactions, budgets, charts, export.

- Test pass rate of 90% or above on all defined test cases.

- UAT sign-off completed with no critical defects outstanding.

11.  APPROVAL & SIGN-OFF

| Prepared By | Nandun De Silva |
| --- | --- |
| Role | Project Manager & Lead Developer |
| Date | March 2026 |
| Version | v1.0 — Initial Release |
| Status | Approved |

This Project Charter formally authorises the Spendly project to proceed. All stakeholders acknowledge the objectives, scope, deliverables, and timeline defined in this document.